## Nine Dimensions
Feature Nine-Dimension Progress Matrix
One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages.
Dimension | Average | 100% features | Applicable features | Primary gap
Design doc | 100% | 6 | 6 | File behavior changes into a functional source
Numeric table | 86% | 3 | 5 | Resolve values that would force implementation guesses
Code | 30.83% | 1 | 6 | Implement the real behavior path
Scene | 21.67% | 0 | 3 | Produce or configure required scenes
UI | 43% | 1 | 5 | Define required interaction and feedback
Icon/image | 51% | 0 | 5 | Produce final-quality visual assets
Scene integration | 8.333% | 0 | 3 | Place approved scenes in runtime
Image integration | 17% | 0 | 5 | Bind approved images to runtime behavior
UI integration | 34% | 1 | 5 | Complete functional UI behavior
Feature total | 6 | 0 | 49.17% | Overall averages applicable dimensions per feature
Feature ID | Complete feature | Source type | Functional source | Numeric/config source | Producer directive | Priority | Design doc | Numeric table | Code | Scene | UI | Icon/image | Scene integration | Image integration | UI integration | Overall | Current stage | Owner | Next milestone | Blocker/dependency
F-001 | Core movement loop | Document + config | docs/features/F-001.md | config/F-001.csv | Playable through the normal entry path | P0 | 100% | 100% | 65% | 25% | 50% | Not needed | 25% | Not needed | 50% | 59.29% | Playable framework | Engineering | Normal gameplay acceptance | Final scene pending
F-002 | Inventory pickup feedback | Document + config | docs/features/F-002.md | config/F-002.csv | Use final icon when available | P1 | 100% | 100% | 20% | Not needed | 40% | 70% | Not needed | 10% | 20% | 51.43% | Contract ready | Design / Engineering | Implement real pickup chain | Shared HUD window
F-003 | First combat slice | Document + config | docs/features/F-003.md | config/F-003.csv | Engineering may use dev-only UI placeholders | P2 | 100% | 80% | 0% | 0% | 25% | 50% | 0% | 0% | 0% | 28.33% | Design complete | Design / Engineering / Art | Create implementation task | Combat runtime not started
F-004 | Final environment art integration | Filed producer directive | docs/features/F-004.md | config/environment-map.csv | Mechanical pass goes directly to development preview | P2 | 100% | 50% | 0% | 40% | Not needed | 60% | 0% | 0% | Not needed | 35.71% | Art production | Art / Engineering | Playable scene preview | Looping master not approved
F-005 | Release placeholder cleanup | Workflow rule | docs/WORKFLOW.md | asset manifest | No dev-only assets in release | P3 | 100% | 100% | 0% | Not needed | 0% | 0% | Not needed | 0% | 0% | 28.57% | Queued | Engineering / Art | Run release scan | Final assets incomplete
F-ZC-AUTH-001 | Player account identity, username, avatar and credential copy | General design DOCX + runtime code + review board | docs/PLAYER_ACCOUNT_IDENTITY_AVATAR_DESIGN_v2.0.docx | Not needed | Keep account ID stable; username is an independent display name; retain direct login and three credential copy actions | P0 | 1 | Not needed | 1 | Not needed | 1 | 0.75 | Not needed | 0.75 | 1 | 0.91667 | Local implementation complete | Design / Engineering / Art | Producer approval for the human avatar board; production auth hardening | FigJam unavailable; human portraits NOT_RUNTIME; KDF/TLS/rate-limit/Aliyun authorization pending
F-ZC-HOME-001 | 动物家园与每日收益 | Filed producer request + DOCX + CSV | docs/HOMESTEAD_DESIGN_v1.1.docx | config/tables/home_economy.csv; config/tables/home_buildings.csv | 无建筑升级；按圈数固定外观；足额点击解锁；最多补领3天；解锁赠1券 | P1 | 0.9 | 1 | 1 | Not needed | 1 | 1 | Not needed | 1 | 1 | 0.98571 | Staging home deployed; local UI validated | codex-primary | External authenticated end-to-end acceptance; Android device acceptance | No real-account writes; external authenticated probe blocked by policy; Figma pending; Android not run
F-ZC-GACHA-NEW-001 | 新动物品质揭晓与特写 | Filed producer request + DOCX + code | docs/HOMESTEAD_DESIGN_v1.1.docx | Existing card rarity definitions | 全品质首次获得演出；柔和惊喜音；抽卡不显示等级和升级信息 | P1 | 0.9 | Not needed | 1 | Not needed | 1 | 1 | Not needed | 1 | 1 | 0.98333 | Local runtime validated | codex-primary | Android export/device acceptance | All 4 qualities and 60 heroes verified; owned duplicates do not trigger new-hero reveal; Figma pending; Android not run

## Overview
Project Progress Overview
Active features | Exceptions | Ready roles | Next work
8 | 0 | 1 | Use Nine Dimensions sheet order

## Active Batch
Active Batch
Priority | Task | Task ID | Owner | State | Last verified progress | Next milestone | Exception

## Role Capacity
Role Capacity
Role | Role ID | Load | Availability | Next assignment | Producer action

## Update Rules
Update Rules
Rule | Current behavior | Owner | Formal source
Exception check | Short interval; current batch only; healthy checks quiet | PM execution operator | docs/active_scope.yaml
Workbook refresh | Every 6 hours or on producer request; save only changes | PM execution operator | docs/active_scope.yaml
Work order | Priority first; same priority by feature ID; completed last | Producer | PM/feature_progress.xlsx
Not applicable | Display Not needed and exclude from averages | PM execution operator | Nine Dimensions
Write boundary | Operator writes only this workbook | PM execution operator | docs/WORKFLOW.md